## RTM
Project Name : Fall Detection System Using Sensors Embedded In Smartphones
#BR | Business Requirement | #FR | Functional Requirement | Description | Test Scenario | Test Result | Signature
BR_1 | Interface | FR_1 | Login/Logout by user | User should be able to login to the application and also logout from the application. | Validation of user's credentials. |  | Vidya
|  | FR_2 | Provide Contact Details | Should be able to provide emergency contact details and also personal details | During emergency, the contact provided by user as emergency must be used. |  | Vidya
|  | FR_3 | Acknowledgement from user | Obtain appropriate acknowledgement from the user, that the user is well incase of fall detection | Provide and validate the acknowledgement by the system |  | Vineeth
BR_2 | Activity Monitoring System | FR_1 | Accessing the appropriate sensor to get data. | Read data from appropriate sensors like accelerometer to obtain data for fall detection | Validate the data obtained. |  | Vidya, Vineeth, Jathin
|  | FR_2 | Fall Detection | Determine the fall based on the readings from the sensors and use the pre-defined time to detect any further activity and decide the future action. | Validate fall detection. |  | Vidya, Vineeth, Jathin
|  | FR_3 | Alarm | Provide alarm when fall is detected | Validate the alarm sound on fall. |  | Vineeth
|  | FR_4 | SMS Alret | Send sms alert to emergency contact | Test the sms alert when fall is detected |  | jathin
|  | FR_5 | Location | Attach location along with sms alert | Test for accuracte location along with sms alert |  | Jathin

## Project Plan
Project Name: Insulin/Glucagon Pump System |  | Planned |  | Actual |  |  | % Completed
Milestone | Activity | Start Date | Duration | Start Date | End Date | Duration
Requirement Analysis | Project Initiation and Planning | 2019-11-25 | 3 | 2019-12-01 | 2019-12-03 | 3 | 70
| Requirement Gathering | 2019-11-29 | 2 | 2019-12-04 | 2019-12-05 | 2 | 90
| Safety Analysis | 2019-12-01 | 3 | 2019-12-06 | 2019-12-07 | 2 | 60
| Hazard Analysis | 2019-12-04 | 2 | 2019-12-08 | 2019-12-08 | 1 | 70
Process Plan | Process Model | 2019-12-06 | 3 | 2019-12-09 | 2019-12-10 | 2 | 80
| Cost Estimation Model | 2019-12-09 | 3 | 2019-12-11 | 2019-12-12 | 2 | 50
| Mathematical Model | 2019-12-09 | 5
System Design | System Design | 2019-12-11 | 2 | 2019-12-11 | 2019-12-12 | 1 | 80
| Model Design | 2019-12-11 | 2 | 2019-12-11 | 2019-12-12 | 1 | 80
High Level Design | Software Design | 2019-12-16 | 9
| UI Design | 2019-12-16 | 9
Implementation | Coding | 2020-12-25 | 16
| Integration | 2020-01-10 | 10
Testing | Unit Testing | 2020-01-20 | 3
| Integration Testing | 2020-01-23 | 4
| System Testing | 2020-01-28 | 5
| Acceptance Testing | 2020-01-30 | 2
Closure | Documentation | 2020-01-25 | 12
| Release | 2019-02-07 | 1

## Hazard Analysis
Hazard Analysis
Hazard | Severity | Occurance | Detection | Control Measures | Risk Priority Number
Insulin / Glucagon not injected | 10 | 5 | 8 | Override to manual injection/ Insulin or glucagon level is checked. | 400
Insufficeint Insulin / Glucagon | 7 | 5 | 7 | Inform user of low insulin/glucagon level | 245
Improper dosage calculation of insulin / glucagonto be injected | 10 | 3 | 8 | Algotrithm is tested for all possible scenarios, logging of activity | 240
Insufficient Battery | 6 | 5 | 8 | Inform user of low battery | 240
Incorrect calculation of blood glucose level | 10 | 3 | 6 | Algotrithm is tested for all possible scenarios, logging of activity | 180
Unstable System | 8 | 2 | 7 | Periodic maintenance/check of the system hardware and update of system software | 112