## Sheet1
Function type | Simple | Average | Complex
External Input | 3 | 4 | 6
External Output | 4 | 5 | 7
External Inquiry | 3 | 4 | 6
Internal Logical File | 7 | 10 | 15
External Interface File | 5 | 7 | 10
[5 empty] | File Type | Function Point | Weighing Factor |  |  | Count
[7 empty] | Simple | Average | Complex
[5 empty] | External Input | login | 3 |  |  | 6
[6 empty] | userAcknowledgment | 3
[5 empty] | External Output | smsAlert | 4 |  |  | 4
[5 empty] | External Inquiry | retriveContact | 3 |  |  | 3
[5 empty] | Internal Logical File | initiate | 7 |  |  | 32
[6 empty] | calculate |  | 10
[6 empty] | detectFall |  |  | 15
[5 empty] | External Interface Files | saveDetails | 5 |  |  | 10
[6 empty] | saveContact | 5
[5 empty] | Total |  |  |  |  | 55
|  |  |  | Value |  | TDEV | Programmer Productivity | Development Time (Month)
Total Unadjusted Function Points (UFP) |  |  |  | 55
Product Complexity Adjustment (PC) = (0.65 + (0.01 * tcav)) |  |  |  | 0.77 |  | Organic | PM = 2.4 * (KLOC) 1.05 | DEV = 2.5 * (PM) 0.38
Total Adjusted Function Points (FP) |  |  |  | 42.35 |  | Semi Detached | PM = 3.0 * (KLOC) 1.12 | DEV = 2.5 * (PM) 0.35
Language Factor (LF) for Java assumed as |  |  |  | 38 |  | Embedded | PM = 3.6 * (KLOC) 1.20 | DEV = 2.5 * (PM) 0.32
Source Lines of Code (SLOC) |  |  |  | 1609.3
[6 empty] | PM = 2.4 * (KLOC) 1.05 | 3.9553 | person-month
[5 empty] | DEV = 2.5 * (PM) 0.38 |  | 4.2157 | month

## Sheet2
Number | Complexity Weighting Factor | Value
1 | Backup and recovery | 0
2 | Data communications | 3
3 | Distributed processing | 0
4 | Performance critical | 3
5 | Existing operating environment | 0
6 | On-line data entry | 0
7 | Input transaction over multiple screens | 0
8 | Master files updated online | 0
9 | Information domain values complex | 3
10 | Internal processing complex | 3
11 | Code designed for reuse | 0
12 | Conversion/installation in design | 0
13 | Multiple installations | 0
14 | Application designed for change | 0
| Total complexity adjustment value | 12